## Gannt Data
Task | Start | Duration
Merge/Set up Repositories | 0 | 1 | 1
Initial Discussion | 0 | 1 | 1
Create launch file for webcam | 0 | 1 | 1
Install OpenCV | 0 | 2 | 2
Implementing CV Bridge Node | 2 | 3 | 5
Planning | 4 | 1 | 5
Install OpenNI | 5 | 0.5 | 5.5
Understand Kinect Data | 5 | 1 | 6
C++ OpenCV Node (Face Detection) | 6 | 7 | 13
Create Size/Depth Model | 9 | 4 | 13
Control Node | 6 | 14 | 20
Tuning PRM (Object Detection) | 13 | 2 | 15
Exploration | 15 | 1 | 16
Room Scanner | 16 | 1 | 17 | Days taken to complete programming:
Testing | 15 | 3 | 18 | 20
Experiments | 20 | 8 | 28
Report Outline | 21 | 2 | 23
Start Assignment: | Demo Date: | Days:
2012-11-16 | 2012-12-06 | 20
Today: | Days from Demo Date to Now:
2013-01-07 | 32