## Sheet1
Task | Start | Duration
Merge/Set up Repositories | 1 | 1
Create launch file for webcam | 0 | 1
Using CV Bridge | 0 | 2
Install OpenCV | 2 | 2
Planning | 4 | 1
Install OpenNi | 3 | 0.5
Understand Kinect Data | 3 | 1
C++ OpenCV Node (Face Detection) | 4 | 4
Create Size/Depth Model | 8 | 3
Control Node | 9 | 5
Tuning PRM (Object Detection) | 10 | 3
Exploration | 13 | 4
Room Scanner | 14 | 2
Testing | 17 | 4