**Team Project: Log Sheet**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Deliverable Summary** | **Assigned Team Member** | **Estimated Hours To Complete** | **Target Completion Date** | **Date Completed** | **Actual Hours Taken** |
| Merge/Set up Repositories | 951926, 1024072 | 24 | 16-Nov-12 | 17-Nov-12 | 12 |
| Initial Discussion | 951926, 1024072, 1001231, 1028907 | 24 | 16-Nov-12 | 17-Nov-12 | 12 |
| Create launch file for webcam | 951926, 1024072 | 24 | 16-Nov-12 | 17-Nov-12 | 12 |
| Install OpenCV | 1001231, 1028907 | 48 | 16-Nov-12 | 18-Nov-12 | 6 |
| Implementing CV Bridge Node | 951926, 1024072, 1001231, 1028907 | 72 | 19-Nov-12 | 21-Nov-12 | 24 |
| Planning | 951926, 1024072, 1001231, 1028907 | 24 | 21-Nov-12 | 21-Nov-12 | 24 |
| Install OpenNI | 951926, 1024072 | 12 | 21-Nov-12 | 21-Nov-12 | 12 |
| Understand Kinect Data | 951926, 1024072, 1001231, 1028907 | 24 | 21-Nov-12 | 22-Nov-12 | 6 |
| C++ OpenCV Node (Face Detection) | 1001231, 1028907 | 168 | 24-Nov-12 | 29-Nov-12 | 48 |
| Create Size/Depth Model | 1001231, 1028907 | 96 | 26-Nov-12 | 29-Nov-12 | 24 |
| Control Node | 951926, 1024072, 1001231, 1028907 | 336 | 27-Nov-12 | 06-Dec-12 | 120 |
| Tuning PRM (Object Detection) | 1001231, 1028907 | 48 | 30-Nov-12 | 01-Dec-12 | 24 |
| Exploration | 1001231, 1028907 | 24 | 02-Dec-12 | 02-Dec-12 | 24 |
| Room Scanner | 951926, 1024072, 1001231, 1028907 | 24 | 02-Dec-12 | 03-Dec-12 | 2 |
| Testing | 951926, 1024072, 1001231, 1028907 | 72 | 04-Dec-12 | 04-Dec-12 | 72 |
| Experiments | 951926, 1024072, 1001231, 1028907 | 192 | 11-Dec-12 | 14-Dec-12 | 120 |
| Report Outline | 1028907 | 48 | 09-Dec-12 | 09-Dec-12 | 48 |